## sample product backlog
As the
ID | Pri | user.. | I want… | Estimate | Status
1 | 1 | player | to control my car's speed and direction on the track so that I can win the race. |  | In progress
5 | 2 | player | to have a variety of terrain/tracks to race on.
6 | 3 | designer | to be able to adjust each recipe's heating requirements so I can tune cakes, engines, and tracks.
2 | 4 | player | to see my engine heat clearly and how it affects my cake's cooking so that I can succesfully bake my cake.
3 | 5 | player | to have several cars to choose from so that I can have more choice in cooking/winning.
4 | 5 | player | to have several cake recipes to choose from so that I can try different cakes w/different engines.

## sprint tasks
Release Goal: Get a racing sandbox built to test physics, car handling in further iterations.
ID | Pri | Status | Task | Type | Estimate | Who
1 | 2 |  | Need a single level/track for the 'car' to race on. | Design
2 | 1 |  | Implement simple driving physics for 'car' | Code
3 | 1 |  | Need a 'box' to drive around the track. | Asset
4 | 2 |  | Need a User Interface/keys for turning car, accelerating/decelerating. | Design
5 | 3 |  | Need a "Track Over" indication. | Code (popup)
6 | 3 |  | Need a "Start Track" button. | Code/Asset